## tails
Capgemini Technology Services India Ltd
Documents Control Section
Project Details
| Project Name | FOOD WASTE MANAGEMENT APPLICATION |  | Project Id
Project Revision History
| Date | Version | Author | Brief Description of Changes | Approver Signature
| 2022-10-21 | Version 0.0 | Group 3 | Mapped requirments with code
Using eSkills Matrix Tool for Skill Tracking
Not using eSkills Matrix Tool for Skill Tracking

## oject Information
Capgemini Technology Services India Ltd
Project Id | Group 3 | Project Name | Food Waste Management Application
Program / Module / Function Name |  | Tested by | Group 3
Platform / Browser / Environment | Vi Editor | Author | Group 3
Type of Testing | Manual Testing | Iteration II Date
Iteration I Date |  | Test Technique | Test case

## gical IT TestCases
*Mandatory to be filled by Testing projects
IT TEST CASES
| Module | Test Case Id | Test Description | Expected Result | Tracebility | Test Situation
| NGO Module | IT_TEST_CASE-01 | User try to edit details with inavalid registration Id | Prints"Given registration Id is not in the list" | Req ICS_02 | Pass
|  | IT_TEST_CASE-02 | User try to view details with inavalid registration Id | Prints"Given registration Id is not in the list" | Req ICS_03 | Pass
|  | IT_TEST_CASE-03 | User try to add details with invalid registration Id | Prints"Given registration Id is not in the list" | Req ICS_01 | Pass
| Hotel Module | IT_TEST_CASE-04 | User try to add details with invalid registration Id | Prints"Given registration Id is not in the list" | Req ICS_04 | Pass
|  | IT_TEST_CASE-05 | User try to edit details with inavalid registration Id | Prints"Given registration Id is not in the list" | Req ICS_05 | Pass
|  | IT_TEST_CASE-06 | User try to view details with inavalid registration Id | Prints"Given registration Id is not in the list" | Req ICS_06 | Pass
|  | IT_TEST_CASE-07 | User try to give report of the food requests | Prints"No requests yet" | Req ICS_15 | Pass
|  | IT_TEST_CASE-08 | User try to delete details with invalid registration Id | Prints"Given registration Id is not in the list" | Req ICS_09 | Pass
|  | IT_TEST_CASE-09 | User try to request the food with invalid registration Id | Prints"Given registration Id is not in the list" | Req ICS_17 | Pass
Admin Module

## _<ModuleXX>_TestCases
Capgemini Technology Services India Ltd
UT TEST CASES
*Mandatory for all lifecylces
Test Case Id | Step | Preconditions / Dependencies | Scenario Description / Test Case | Test Data | Expected Result | Actual Result (Iteration I) | Status (Pass or Fail) | Bug Severity | Comments/Defect No. | Actual Result (Iteration II) | Status (Pass or Fail)
FWM_REG_01 | Enter NGO Registration id | NGO should provide valid registration id | User enters Registration id of length 5 | Registration id -12345 | Registration Id should be 5 numeric digits | Registration id is 5 numeric digits | Pass | No |  | Registration id is 5 numeric digits | Pass
FWM_REG_02 | Enter Hotel Registration id | Hotel should provide valid registration id | User enter Registartion Id od length 5 | Registartion id-abc67 | Registration Id should be 5 numeric digits | Registration id is 5 non numeric digits | Fail | Minor | Invalid input | Registration idshould be 5 numeric digits | Pass
FWM_REG_03 | Enter NGO Registration id by admin | NGO should provide valid registration id | User enters Registration id of length 5 | Registration id-23456 | Registration Id should be 5 numeric digits | Registration id is 5 numeric digits | Pass | No |  | Registration id is 5 numeric digits | Pass
FWM_REG_04 | Enter Hotel Registration id by admin | Hotel should provide valid registration id | User enters Registration id of length 5 | Registration id-73456 | Registration Id should be 5 numeric digits | Registration id is 5 numeric digits | Pass | No |  | Registration id is 5 numeric digits | Pass
FWM_REG_05 | Enter NGO name | Valid NGO name should be entered | User enters name less than 50 characters | Name-Patel | Name must be less than 50 characters. | Name must be less than 50 characters | Pass | No |  | Name must be less than 50 characters | Pass
FWM_REG_06 | Enter Hotel name | Valid Hotelname should be entered | User enters name less than 50 characters | Name-Bhagat | Name must be less than 50 characters. | Name must be less than 50 characters | Pass | No |  | Name must be less than 50 characters | Pass
FWM_REG_07 | Enter Contact number | Valid contact number should be entered | User enters valid contact number | Contact No:9876543218 | User conatct number will be added to the registration details | User contact number will be added to the registration details | Pass | No |  | User contact number will be added to the registration details | Pass
FWM_REG_08 | Enter user register id to edit conatct number | Check for the user with given register Id | User enters valid register id | Registartion id-xyz67 | User registration id not found | Registration id is 5 non numeric digits taht should be in the record | Fail | Minor | Invalid Id | User is unable to identify with given Register id | Fail
FWM_REG_09 | Enter user register id to edit address | Check for the user with given register Id | User enters valid register id | Registration id -12345 | User address should be less than 50 characters | User address is less than 50 characters | Pass | No |  | User is able to change the address | Pass
FWM_REG_10 | Enter the NGO registration id to delete the record | Check for the user with given register Id | User enters valid register id | Registration id-23456 | User able to delete the record | User record is deleted | Pass | No |  | User record is deleted | Pass
FWM_REG_11 | Enter the Hotel registration id to view the record | Check for the user with given register Id | User enters valid register id | Registration id-73456 | User able to view the record | User is able to view the record | Pass | No |  | User is able to view the record | Pass
FWM_REG_12 | Enter the NGO registration id to request the food | Check for the user with given register Id | User enters valid register id | Registration id -12345 | User is able to request food | User is able to connect | Pass | No |  | User is able to request the food | Pass